## Backlogs
Sl. No. | Items | Examples
1 | Add {institue_id} to API endpoints, like Classes, Users, Questions, Exams | /api/v1/institutes/{institute_id}/Classes /api/v1/institutes/{institute_id}/Classes/{class_id} /api/v1/institutes/{institute_id}/Classes/{class_id}/Users /api/v1/institutes/{institute_id}/Classes/{class_id}/Subjects /api/v1/institutes/{institute_id}/Exams /api/v1/institutes/{institute_id}/Users /api/v1/institutes/{institute_id}/Questions
2 | Add language or locale to API endpoints
3 | Add versioning as parameter to API endpoints before {institute_id}
4 | Add filtering mechanisms to API enddpoints, as query parameter like; sorting, searching, pagination, is_active, is_delete, by_name, created_on, updated_on

## Timeline
Month |  |  |  | June |  |  |  | July
Tasks | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15
Initiation
Planning
Execution
Testing
Monitoring
Closeout
API
Web UI

## WBS
WORK BREAKDOWN STRUCTURE
1 | ONLINE ASSESSMENT
1.1 | INITIATION
1.2 | PLANNING
1.3 | EXECUTION
| 1.3.1 | DEVELOP SOFTWARE
|  | 1.3.1.A | USER MODULE
|  |  | 1.3.1.A.1 | SIGN IN
|  |  | 1.3.1.A.2 | SIGN UP
|  | 1.3.1.B | SUPER ADMIN MODULE
|  |  | 1.3.1.B.1 | PLANS
|  |  | 1.3.1.B.2 | SUBSCRIPTIONS

## WBS-WorkItems
WorkItem ID
User Module (1.3.1.A) |  | Super Admin Module (1.3.1.B) |  | Institute Admin (1.3.1.C) |  | Teacher (1.3.1.D)
Signin 131A1 |  | Institutes (131B1) |  | Admin - Teacher (131C1) |  | Teacher-Questions (131D1)
131A11 | Signin API Devlopment | 131B11 | Institue API development | 131C11 | Admin-Teacher API development | 131D11 | API
131A12 | Signin UI Devlopment | 131B12 | Institue UI development | 131C12 | Admin-Teacher UI development | 131D12 | UI
131A13 | Testing | 131B13 | Institue Testing | 131C13 |  | 131D13 | Testing
131A13.1 | Singin API Testing | 131B13.1 | Institue API Testing
131A13.2 | Signin UI Testing | 131B13.2 | Institue UI Testing
131A14 | Signin Automation | 131B14 | Institute Automation | 131C14 |  | 131D14 | Automation
Signup 131A2 |  | Dashboard (131B2) |  | Students - (131C2) |  | Teacher-Exam (131D2)
131A21 | Signup API Devlopment | 131B21 | Super Admin Dashboard API development |  | API | 131D21 | API
131A22 | Signup UI Devlopment | 131B22 | Super Admin Dashboard UI developoment |  | UI | 131D22 | UI
131A23 | Signup Testing | 131B23 | Super Admin Dashboard Testing |  | Testing-API | 131D23 | Testing
131A23.1 | Signup API Testing | 131B23.1 | Super Admin Dashboard API Testing |  | Testing-UI
131A23.2 | Signup UI Testing | 131B23.2 | Super Admin Dashboard UI Testing |  | Automation
131A24 | Signup Automation | 131B24 | Super Admin Dashboard Automation | Keys -Categories (131C3) |  | 131D24 | Automation
Profiles 131A3 |  |  |  |  | API | Teacher-Evaluation (131D3)
131A31 | Profiles API Devlopment | Master Files (131B4) |  |  | UI | 131D31 | API
131A32 | Profiles UI Devlopment | 131B41.1 | Roles API development |  | Testing-API | 131D32 | UI
131A33 | Profiles Testing | 131B41.2 | Roles API Testing |  | Testing-UI | 131D33 | Testing
131A33.1 | Profiles API Testing
131A33.2 | Profiles UI Testing
131A36 | Profiles Automation | 131B42.1 | States API development |  | Automation | 131D34 | Automation
Change Password 131A4 |  | 131B42.2 | States API Testing | Keys -SubCategories (131C4)
131A41 | Change Password API Devlopment | 131B43.1 | Plans API development |  | API
131A42 | Change Password UI Devlopment | 131B43.2 | Plans API Testing |  | UI
131A43 | Change Password Testing | 131B44.1 | Subscriptions API development |  | Testing
131A43.1 | Change Password API Testing
131A43.2 | Change Password UI Testing
131A44 | Change Password Automation | 131B44.2 | Subscription API Testing |  | Automation
Forget Password 131A4 |  | 131B45.1 | Question Types API development
131A51 | Forget Password API Devlopment | 131B45.2 | Question Types API Testing | Keys -Classes (131D4)
131A52 | Forget Password UI Devlopment | 131B46.1 | Exam Types API development |  | API
131A53 | Forget Password Testing | 131B46.2 | Exam Types API Testing |  | UI
131A53.1 | Forget Password API Testing
131A53.2 | Forget Password UITesting
131A54 | Forget Password Automation | 131B47.1 | Exam Practice Types API development |  | Testing
Signout 131A5 |  | 131B47.2 | Exam Practice Types API tesging |  | Automation
131A61 | Signout API Devlopment |  |  | Keys -Subjects (131E4)
131A62 | Signout UI Devlopment |  |  |  | API
131A63 | Signout Testing |  |  |  | UI
131A63.1 | Signout API Testing
131A63.2 | Signout UI Testing
131A64 | Signout Automation |  |  |  | Testing
Automation

## WBS API Progress
|  | Status (Dev) | Status (Test)
131A11 | Signin API Devlopment
131A21 | Signup API Devlopment
131A31 | Profiles API Devlopment
131A41 | Change Password API Devlopment
131A51 | Forget Password API Devlopment
131A61 | Signout API Devlopment

## DB-Language
Plan | Subscription | Institute | Language Table | Roles |  | User info table | Key: Class table | Key : Subject Table | Key : Category Table | Key : Sub Category Table | Key: Tags table | Key : Question Type table |  | Class user table |  | Subject User Table | Questions Table | Question option table | Question tags table | Question Sub Category table | Exam Type Table |  | Exam Table |  | Exam Section Table |  | Questions In Exam | Exam Students |  | Student Answer | Student assessment | Practice Type Table |  | Exam Practice Table |  | Questions In Practice | Practice Students | Student Answer |  | Bookmark Question Table | Bookmark Exam Table | Bookmark Practice Table | Bookmark Notes Table | Activity log table |  | Study Notes Table |  | Note tags table | Modules table |  | Module_role Table
[6 empty] | User to Institute is 1 to 1 User to User Role is 1 to1 But one user can be part of multiple Classes or Subjects | [10 empty] | Question is lowest most entity and kept as independent. Can be associated with multiple Tags & multiple Sub categories | [13 empty] | Requied for Subjective type | Unlike Exams it will have only one section | [18 empty] | Role Based Access control
once u start exam id will be created
Plan ID | Subscription ID | institute ID | Language ID | User Role ID |  | User ID | Class ID | Subject ID | Category ID | Sub Category ID | Tags ID | Question Type ID |  | Class ID |  | Subject ID | Question ID | Question option ID | Tags ID | Sub Category ID | ExamType ID |  | Exam ID |  | Exam Section ID |  | 0 | Attempt id |  | Student Answer ID | Student Answer ID | Practice Type ID |  | Practice ID |  | Practice ID | PracticeStudent ID | Student Answer ID |  | BookmarkQ ID | BookmarkE ID | BookmarkP ID | BookmarkN ID | User ID |  | Note ID |  | Tags ID | Module ID |  | Module Role ID
Name | Plan Id | Name | Language | User Role Text | Super Admin, Admin, Student, Teacher, Guest | User Role ID | Institiute ID | Class ID | Subject ID | Category ID | Category ID | Question type text | MCQ/Subjective/Truefalse | User ID |  | User ID | Question Type ID | Question ID | Question ID | Question ID | Exam type text | Complete / Subject based/Previous year | Exam Type ID |  | Exam ID |  | Question ID | Exam ID |  | Attempt ID | Valid Answer ID | Practice type text | Exam type/ Question timer / Without Option | Practice Type ID |  | Question ID | Practice ID | Practice ID |  | User ID | User ID | User ID | User ID | Action | Added/created/Appeared/deleted/attempted/cloned | User ID | Author | Note ID | Name | Exam,Questions,Practice, Notes, User | Module ID
Desc | Institute ID | domain |  |  |  | Institiute ID | Image | Image | Image | Image | Image |  |  | User Role ID | It ll help in computation | User Role ID | Question_status | Option image |  |  |  |  | Exam Status | draft/published/inactive | Subject ID |  | Mark | User ID |  | Question ID | Student Answer |  |  | Status | draft/published/inactive | Mark | User ID | Question ID |  | Question ID | Exam ID | Practice ID | Note ID | Item Type | Exam ID, Qns ID, User ID, others | Subject ID |  |  | Description |  | UserType ID
Duration Days | is_active | api_key |  |  |  | Registration ID | is_active | is_active | is_active | is_active | is_active | [5 empty] | Question Image | [5 empty] | UserGroup ID | published to a group of students | User ID | Author | Negative mark | Attempted count |  | Date of Answer | Correctness |  |  | UserGroup ID |  | Negative mark | Score | USER ID |  | bookmarked date | bookmarked date | bookmarked date | bookmarked date | Item |  | Category ID | if null, Note is for above Subject |  | created_on |  | isAdd
Created_at | start_time | date of establishment |  |  |  | Email ID | created_on | created_on | created_on | created_on | created_on | [5 empty] | User ID | [5 empty] | Exam Open Time |  | Subject Sequence |  | Question Sequence | Exam User Staus | show / hidden | Time taken | Assessment |  |  | Total Duration |  |  | Avg time taken | Date of Answer | [5 empty] | Action date |  | Sub Category ID | if Null, Note is for above Category |  | updated_on |  | isView
last_updated on | end_time | address |  |  |  | Mobile | updated_on | updated_on | updated_on | updated_on | updated_on | [5 empty] | Source | Question option table trans |  |  |  |  | Exam Close time |  | Subject Duration |  |  | Assessment Status | To be verified by teacher ? | Comments |  |  |  | Question duration |  |  | Started on | Time taken | [7 empty] | Name |  |  |  |  | isEdit
| created_at | city |  |  |  | Password |  |  |  | pdf_url | pdf_url | [5 empty] | Complexity | Question option ID |  |  |  |  | Exam Duration |  | Total Mark |  |  | Score |  | Correctness |  |  |  | created by ID | Author |  | Completed on | Comments | [7 empty] | Description |  |  |  |  | isDelete
| last_updated_on | state |  |  |  | First name |  |  |  | video_url | video_url | [5 empty] | created_on | Language ID |  |  |  |  | Attempts allowed |  |  |  |  | Time taken |  | Student Answer |  |  |  | Created Date |  |  |  | Correctness | [7 empty] | pdf_url
|  | country |  |  |  | Last name | Key: Class table trans | Key: Subject table trans | Key: Category table trans | [7 empty] | updated_on | Option text |  |  |  |  | created by ID | Author |  |  |  | Started on |  | Doubt |  |  |  | Updated Date |  |  |  | Student Answer | [7 empty] | video_url
|  | Image |  |  |  | Date Of Birth | Class ID | Subject ID | Category ID | [7 empty] | question answer id | [5 empty] | Created Date |  |  |  |  | Completed on | [5 empty] | Complexity |  |  |  | Doubt | [7 empty] | status
|  | is_active |  |  |  | Registration date | Language ID | Language ID | Language ID | [7 empty] | pdf_url | [5 empty] | Updated Date |  |  |  |  | State | Start/pause/resume/completed |  |  |  |  | Image |  |  |  | Score | in case score is based on time taken | [6 empty] | UserGroup ID
|  | created_on |  |  |  | Regstration time | Name | Name | Name | Key: Sub category table trans | Key: Tags table trans | [5 empty] | video_url | [5 empty] | Need Assessment | Yes if subjective type qns | [9 empty] | Total mark | [11 empty] | is_active
|  | updated_on |  |  |  | address | Description | Description | Description | Sub Category ID | Tags ID | [5 empty] | Institute ID | [5 empty] | Complexity | [10 empty] | Institute ID | [11 empty] | created_on
[6 empty] | city |  |  |  | Language ID | Language ID | [5 empty] | best duration | [5 empty] | Image | [22 empty] | updated_on
[6 empty] | state |  |  |  | Name | Name | [5 empty] | avg duration | [5 empty] | Total mark
[6 empty] | Last login date |  |  |  | Description | Description | [5 empty] | total attempts | [5 empty] | Institue ID | [10 empty] | Practice Table trans
[6 empty] | Image | [10 empty] | total corrects | [16 empty] | Practice ID
[6 empty] | is_active | [27 empty] | Language ID
[6 empty] | created_on | [10 empty] | Questions Table trans | [5 empty] | Exam Table trans | [10 empty] | Name
[6 empty] | updated_on | [10 empty] | Question ID | [5 empty] | Exam ID | [10 empty] | Description
[17 empty] | Language ID | [5 empty] | Language ID | [10 empty] | Instructions
[17 empty] | Question Text | [5 empty] | Exam Name
[6 empty] | User info table trans | [10 empty] | Question Description | [5 empty] | Exam Description
[6 empty] | User Role ID | [10 empty] | Hint | [5 empty] | Instructions
Language ID
Gender
country

## API
Plan | Subscription | Institute | Language Table | Roles | User table | Key: Class table | Key : Subject Table | Key : Category Table | Key : Sub Category Table | Key: Tags table | Key : Question Type table | Class user table | Subject User Table | Questions Table |  | Question option table | Question tags table | Question Sub Category table | Exam Type Table | Exam Table | Exam Section Table | Questions In Exam | Exam Students | Student Answer | Student assessment | Practice Type Table | Practice Table | Questions In Practice | Practice Students | Student Answer | Bookmark Question Table | Bookmark Exam Table | Bookmark Practice Table | Bookmark Notes Table | Activity log table | Study Notes Table | Note tags table | Modules table | Module_role Table
/plans | /subscriptions/{ID} | institutes/{ID} | /languages | /roles | /users/signin | [8 empty] | questions/all | Get | /questions/{qid}/options |  |  |  | /exams | /exams/{eid}/sections/add | /exams/{eid}/sections/{secid}/addquestion/{qid} | /exams/{eid}/users | /exams/{eid}/users/{uid}/questions/{qid}/answer
/plans/add |  |  | /languages/{ID} | /userroles/{ID} | /users/signup | [8 empty] | /questions/{qid}/detail | Post |  |  |  |  | /exams/{eid}/detail | /exams/{eid}/sections/{secid}/delete | /exams/{eid}/sections/{secid}/deletequestion/{qid} |  | /exams/{eid}/users/{uid}/questions/{qid}/answer
/plans/delete | /subscribe | /institutes/signup | /languages/add | /userroles/add | /users/{ID}/resetlogin | [8 empty] | /questions/update | Post |  |  |  |  | /exams/{eid}/update | /exams/{eid}/sections/ | /exams/{eid}/sections/{secid}/questions |  | /exams/{eid}/users/{uid}/answers
/plans/update | /unsubscribe | /institutes/activate | /languages/delete | /userroles/delete | /users/{ID}/forgotpassword | [8 empty] | /questions/{qid}/hints | [5 empty] | /exams/{eid}/isactive |  |  |  | /exams/{eid}/users/{uid}/correctness
|  | /institutes/update |  |  | /users/{ID}/activateuser | [8 empty] | /questions/{qid}/answer | [5 empty] | /exams/{eid}/duration
|  | /institutes/detachclasses |  |  | /users/{ID}/basicdetails | [8 empty] | /questions/{uid}/all | [5 empty] | /exams/{uid}/all
|  | /institutes/attachusers |  |  | /users/{ID}/details | [8 empty] | /questions/add | [5 empty] | /exams/add
|  | /institutes/detachusers |  |  | /users/{ID}/add | [8 empty] | /questions/{qid}/save | [5 empty] | /exams/{eid}/delete
|  | /institutes/classes |  |  | /users/{ID}/update | [8 empty] | /questions/{qid}/submit | [5 empty] | /exam/{eid}/save
|  | /institute/users |  |  | /users/{ID}/email | [8 empty] | /questions/{qid}/delete | [5 empty] | /exam/{eid}/publish
[5 empty] | /users/{ID}/sms | [8 empty] | /questions/{qid}/attachtag/{tid} | [5 empty] | /exams/{eid}/start
[5 empty] | /users | [8 empty] | /questions/{qid}/detachtag/{tid} | [5 empty] | /exams/{eid}/pause
[5 empty] | /users/{uid}/attachclass/{cid} | [8 empty] | /questions/{qid}/attachsubcategory/{sid}/ | [5 empty] | /exams/{eid}/stop
[5 empty] | /users/{uid}/attachsubject/{cid}/ | [8 empty] | /questions/{qid}/detachsubcategory/{sid} | [5 empty] | /exams/{eid}/submit
[5 empty] | /users/{uid}/detachclass/{cid} | [8 empty] | /questions/{qid}/tags
[5 empty] | /users/{uid}/detachsubject/{cid}/ | [8 empty] | /questions/{qid}/subcategories
[5 empty] | /users/{uid}/classes | [8 empty] | /questions/update/bulk
/users/{uid}/subjects

## Screen-API
Screen | Description | Method | Endpoint | Parameters | Tokens | Status | Comments
Signin/Signup |  | POST | /api/v1/Users/SignIn | email, password |  | Done |  | https://developer.testpress.in/?shell#get-attempt-questions
|  | POST | /api/v1/Users/SignUp |  |  | Done
Users | This endpoint retrieves details of the authenticated user. | GET | /api/v1/institutes/{institute_id}/Users/{id} |  |  | Done
| This endpoint will update a user profile details. | PUT | /api/v1/institutes/{institute_id}/Users/{id} |  |  | Done
| This endpoint will delete specific users | DELETE | /api/v1/institutes/{institute_id}/Users/{id} |  |  | Done
Teachers | This endpoint retrieves questions added by teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions_added
| To retrieve exams created by a teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams_added
| To retrieve students under a teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/students
| To retrieve notes added by a teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes_shared
| To retrieve all teachers of an institute | GET | /api/v1/institutes/{institute_id}/Users/teachers
Students | To retrieve all teachers of an institute | GET | /api/v1/institutes/{institute_id}/Users/students
| To retrieve all teachers of an institute by batch | GET | /api/v1/institutes/{institute_id}/Users/students?batch={user_group}
| This endpoint retrieves question practiced | GET | /api/v1/institutes/{institute_id}/Users/{id}/practice_questions_done
| This endpoint retrieves exams attempted | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams_attempted
| This endpoint retrieves subjects taken | GET
Questions | To add question | POST | /api/v1/institutes/{institute_id}/question |  |  |  | Filter by
| To add question in bulk | POST | /api/v1/institutes/{institute_id}/questions
| To retrieve question in draft | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?subject={teacher-subject}$question_status={draft}
| To update question | PUT | /api/v1/institutes/{institute_id}/question/{question_id}
| To only submit a question | PUT | /api/v1/institutes/{institute_id}/question/{question_id} |  |  |  | question_status={active}
| This endpoint retrieves all questions (Default) | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?subject={teacher-subject}
| This endpoint retrieves all questions by type | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?type={question_type}
| This endpoint retrieves all questions by subject | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?subject={subject}
| This endpoint retrieves all questions by category | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?category={category}
| This endpoint retrieves all questions by tags | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?tags={tags}
| This endpoint retrieves all questions by author | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?author={teacher_id}
| This endpoint retrieves all questions bookmarked by author | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions?author={teacher_id}&bookmarked=True
To bookmark a question
| To delete a question | DELETE | /api/v1/institutes/{institute_id}/question/{question_id}
Exams | To add/create exam | POST | /api/v1/institutes/{institute_id}/exams
| To retrieve exam in draft | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?subject={teacher-subject}$exam_status={draft}
| To update an exam | PUT | /api/v1/institutes/{institute_id}/exams/{exam_id}
| To schedule an exam | PUT | /api/v1/institutes/{institute_id}/exams/{exam_id} |  |  |  | exam_status={published}
| To retrieve all exams under institute | GET | /api/v1/institutes/{institute_id}/exams | subject, title
| To retrieve all exams under institute upcoming | GET | /api/v1/institutes/{institute_id}/exams/upcoming | subject, title
| To retrieve all exams under institute available | GET | /api/v1/institutes/{institute_id}/exams/available | subject, title
| This endpoint retrieves all exams (Default) | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&exam_close_time={>current_time}
| This endpoint retrieves all exams by type | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&exam_type={exam_type}
| This endpoint retrieves all exams by subject | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&subject={subject}
| This endpoint retrieves all exams by category | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&category={category}
To display exams in calender
Exam Attempts | This endpoint retrieves all attempts for the authenticated user. | GET | /api/v1/institutes/{institute_id}/attempts
| This endpoint retrieves the attempts of a user for a particular exam. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts
| This endpoint retrieves a single attempt. | GET | /api/v1/institutes/{institute_id}/attempts/{id}
| This endpoint will create a new attempt for the exam. | POST | /api/v1/institutes/{institute_id}/exams/{id}/attempts
| This endpoint starts a paused attempt. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/start
| This is done to update the remaining time for that attempt in the server. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/heartbeat
| This endpoint ends an attempt. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/end
| This endpoint returns all questions for an attempt. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/questions
| This endpoint will update a question with the selected_answers and review. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/questions/{id}
| This endpoint returns all questions for an attempt with correct answer & explanation. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/review
| This endpoint returns subject wise analytics of the attempt. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/review/subjects
Practice Attempts | This endpoint retrieves all attempts for the authenticated user. | GET | /api/v1/institutes/{institute_id}/practiceattempts
| This endpoint retrieves the attempts of a user for a particular practice. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts
| This endpoint retrieves a single attempt. | GET | /api/v1/institutes/{institute_id}/practiceattempts/{id}
| This endpoint will create a new attempt for the practice. | POST | /api/v1/institutes/{institute_id}/practice/{id}/attempts
| This endpoint starts a paused attempt. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/start
| This is done to update the remaining time for that attempt in the server. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/heartbeat
| This endpoint ends an attempt. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/end
| This endpoint returns all questions for an attempt. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/questions
| This endpoint will update a question with the selected_answers and review. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/questions/{id}
| This endpoint returns all questions for an attempt with correct answer & explanation. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/review
| This endpoint returns subject wise analytics of the attempt. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/review/subjects
Study Notes | This endpoint add notes | POST | /api/v1/institutes/{institute_id}/Users/{id}/notes
| To endpoint retrieve notes in draft | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?author={student_id/teacher_id}$notes_status={draft}
| To endpoint update an notes | PUT | /api/v1/institutes/{institute_id}/Users/{id}/notes/{id}
| To endpoint retrives a single notes | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes/{id}
| This endpoint retrieves all notes (Default) | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?created_by_id={teacher_id}
| This endpoint retrieves notes by class | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?user_group={teacher_group/student_group}
| This endpoint retrieves notes by type | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?user_group={student_user_group}
| This endpoint retrieves notes by subject | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?subject={subject}&user_group={student_user_group}
| This endpoint retrieves notes by author | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?teacher={teacher_id}&user_group={student_user_group}
| This endpoint retrieves notes added by author | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?author={student_id/teacher_id}
Evaluation-Stats
Evaluation
UserGroups (Batches) | This endpoint retrieves all user_groups | GET | /api/v1/institutes/{institute_id}/user_groups
| This endpoint retrieves single user_group | GET | /api/v1/institutes/{institute_id}/user_groups/{id}
| This endpoint will create a user_group | POST | /api/v1/institutes/{institute_id}/user_groups
| This endpoint will delete specific user_group | DELETE | /api/v1/institutes/{institute_id}/Users/{id}
Institute | This endpoint retrieves all classes counts | GET | /api/v1/institutes/{institute_id}/classes_count |  |  |  | To populate dashboard
| This endpoint retrieves all teachers counts | GET | /api/v1/institutes/{institute_id}/teachers_count |  |  |  | To populate dashboard
| This endpoint retrieves all students counts | GET | /api/v1/institutes/{institute_id}/students_count |  |  |  | To populate dashboard
| This endpoint retrieves all subjects counts | GET | /api/v1/institutes/{institute_id}/subjects_count |  |  |  | To populate dashboard
| This endpoint retreives admin profile | GET | /api/v1/institutes/{institute_id}/admin_profile
| This endpoint updates admin profile | PUT | /api/v1/institutes/{institute_id}
| This endpoint delete admin profile | DELETE | /api/v1/institutes/{institute_id}
| This endpoint adds admin profile | POST | /api/v1/institutes/{institute_id}/admin_profile
| This endpoint adds teacher | POST | /api/v1/institutes/{institute_id}/teachers
| This endpoint update teacher |  | Already would have covered
| This endpoint delete teacher |  | Already would have covered
| This endpoint retrieves all teachers |  | Already would have covered
| This endpoint retrieves all subjects |  | Already would have covered
| This endpoint retrieves all classes counts |  | Already would have covered
| This endpoint adds student | POST | /api/v1/institutes/{institute_id}/students
| This endpoint bulk add students | POST | /api/v1/institutes/{institute_id}/bulk_students
| This endpoint update student |  | Already would have covered
| This endpoint delete student |  | Already would have covered
| This endpoint retrieves all students counts |  | Already would have covered
Subjects |  |  | Already would have covered
Category |  |  | Already would have covered
Tags |  |  | Already would have covered
Institute Dashboard
SuperAdmin | Add Institute |  | Already would have covered
| Update Institute |  | Already would have covered
| Delete Institute |  | Already would have covered
| To retrive all institute | GET | /api/v1/institutes
| This endpoint retrieves all institutes counts | GET | /api/v1/institutes_count |  |  |  | To populate dashboard
| This endpoint retrieves all teachers counts | GET | /api/v1/teachers_count |  |  |  | To populate dashboard
| This endpoint retrieves all students counts | GET | /api/v1/students_count |  |  |  | To populate dashboard
| This endpoint retrieves all exams counts | GET | /api/v1/exams_count |  |  |  | To populate dashboard
Others
| This endpoint get students in class/batch | GET | /api/v1/institutes/{institute_id}/Users?user_group={user_group}

## API-Latest
Screen | Access Level | Description | Method | Endpoint | Parameters | Response | Logic
Institute | Admin | This endpoint creates a Institute | POST | /api/v1/Institutes
|  | This endpoint retrives the Institute | GET | /api/v1/Institutes/{id} |  | All institute info, subsription
|  | This endpoint retrives all the Institute | GET | /api/v1/Institutes
|  | This endpoint retrives all the Institute | GET | /api/v1/Institutes/All | isActive, state, city, Sortby: field, sorttype: A/D
|  | This endpoint updates the Institute | PUT | /api/v1/Institutes/{id}
|  | This endpoint deletes the Institute | DELETE | /api/v1/Institutes/{id}
|  | this endpoint retrives the active subscription | GET | /api/v1/Institutes/{id}/activesubscription |  | Institute Name, ID, subscription info
|  | this endpoint retrives subscription history | GET | /api/v1/Institutes/{id}/subscriptions | status, Sortby: field, sorttype: A/D | Subscription info (all)
Signin/Signup |  |  | POST | /api/v1/institutes/{id}/users/SignIn | email, password |  |  | https://developer.testpress.in/?shell#get-attempt-questions
|  |  | POST | /api/v1/institutes/{id}/users/SignUp
Users | Student/teacher | This endpoint retrieves details of the any user. | GET | /api/v1/institutes/{institute_id}/Users/{id} |  | Basic user details without password, Role info, Class info
| Student/teacher | This endpoint retrieves details of the authenticated user. | GET | /api/v1/institutes/{institute_id}/Me |  | Complete User info
Users | Admin | This endpoint creates a user | POST | /api/v1/institutes/{institute_id}/admin/Users |  | Complete User info
| Admin | This endpoint will update any user profile | PUT | /api/v1/institutes/{institute_id}/Users/{id} |  | Complete User info
| Admin | This endpoint will delete specific users | DELETE | /api/v1/institutes/{institute_id}/Users/{id}
Class | Admin | This end point will create class | POST | /api/v1/institutes/{institute_id}/Classes | name, desc, language, isactive
| Admin | This endpoint retrieves details of all classes | GET | /api/v1/institutes/{institute_id}/Classes | language, isactive | Class info
| Admin/Teacher/Student | This endpoint retrieves details of a specific class | GET | /api/v1/institutes/{institute_id}/Classes/{id} |  | Class info, active exams basic, active practices basic
| Admin | This endpoint will update a class | PUT | /api/v1/institutes/{institute_id}/Classes/{id}
| Admin | This endpoint will delete class | DELETE | /api/v1/institutes/{institute_id}/Classes/{id}
| Admin | This endpoint allows you to add users to classes | POST | /api/v1/institutes/{institute_id}/Classes/{id}/users_attach | user id list
Subject | Admin/Teacher | This end point will create Subject | POST | /api/v1/institutes/{institute_id}/Subjects | name, desc, language, isactive
| Admin/Teacher/Student | This endpoint retrieves details of all subjects | GET | /api/v1/institutes/{institute_id}/Subjects | language, isactive,class,teacher | Subject info
| Admin/Teacher/Student | This endpoint retrieves details of a specific subject | GET | /api/v1/institutes/{institute_id}/Subjects/{id} |  | Subject info, Practices info, Notes info
| Admin/Teacher | This endpoint will update a subject | PUT | /api/v1/institutes/{institute_id}/Subjects/{id}
| Admin/Teacher | This endpoint will delete a subject | DELETE | /api/v1/institutes/{institute_id}/Subjects/{id}
| Admin/Teacher | This endpoint allows you to associate subjects to classes | POST | /api/v1/institutes/{institute_id}/classes/{id}/subjects_attach | subject id list
Category | Admin/Teacher | This end point will create Categoty | POST | /api/v1/institutes/{institute_id}/Categories | name, desc, language, isactive
| Admin/Teacher/Student | This endpoint retrieves details of all categories | GET | /api/v1/institutes/{institute_id}/Categories | language, isactive, class,subject,teacher | Category info
| Admin/Teacher/Student | This endpoint retrieves details of a specific category | GET | /api/v1/institutes/{institute_id}/Categories/{id} |  | Category info, Notes info
| Admin/Teacher | This endpoint will update a category | PUT | /api/v1/institutes/{institute_id}/Categories/{id}
| Admin/Teacher | This endpoint will delete a category | DELETE | /api/v1/institutes/{institute_id}/Categories/{id}
| Admin/Teacher | This endpoint allows you to associate categories to subject | POST | /api/v1/institutes/{institute_id}/subjects/{id}/categories_attach | categories id list
Sub Category | Admin/Teacher | This end point will create sub category | POST | /api/v1/institutes/{institute_id}/Subcategories | name, desc, language, isactive
| Admin/Teacher/Student | This endpoint retrieves details of all subcategories | GET | /api/v1/institutes/{institute_id}/Subcategories | language, isactive, class,subject,subcategories,teacher | SubCategory info
| Admin/Teacher/Student | This endpoint retrieves details of a specific subcategory | GET | /api/v1/institutes/{institute_id}/Subcategories/{id} |  | SubCategory info, Notes info
| Admin/Teacher | This endpoint will update a subcategory | PUT | /api/v1/institutes/{institute_id}/Subcategories/{id}
| Admin/Teacher | This endpoint will delete a subcategory | DELETE | /api/v1/institutes/{institute_id}/Subcategories/{id}
| Admin/Teacher | This endpoint allows you to associate subcategories to categories | POST | /api/v1/institutes/{institute_id}/categories/{id}/subcategoies_attach | subcategories id list
| Admin/Teacher | This endpoint allows you to unassociate subcategories to categories | POST | /api/v1/institutes/{institute_id}/categories/{id}/subcategoies_deattach | subcategories id list
Tags | Admin/Teacher | This end point will create tags | POST | /api/v1/institutes/{institute_id}/tags | name, desc, language, isactive
| Admin/Teacher/Student | This endpoint retrieves details of all tags | GET | /api/v1/institutes/{institute_id}/tags | language, isactive, question, notes | Tags info
| Admin/Teacher/Student | This endpoint retrieves details of a specific tag | GET | /api/v1/institutes/{institute_id}/tags/{id} |  | Tags info, Notes info, question info
| Admin/Teacher | This endpoint will update a tag | PUT | /api/v1/institutes/{institute_id}/tags/{id}
| Admin/Teacher | This endpoint will delete a tag | DELETE | /api/v1/institutes/{institute_id}/tags/{id}
Questions | Admin/Teacher | To add question | POST | /api/v1/institutes/{institute_id}/question | language, Qns text, Qns type, isactive, options, answer | Filter by
| Admin/Teacher | To add question in bulk | POST | /api/v1/institutes/{institute_id}/questions | language, Qns text, Qns type, isactive, options, answer - list
| Admin/Teacher | To retrive my questions | GET | /api/v1/institutes/{institute_id}/Me/questions | language, bookmark, Subject, Category, sub category, tags, author, status, complexity, title text
| Admin/Teacher | To retrive others questions | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions | language, Subject, Category, sub category, tags, author, status, complexity, title text | questions basic info
| Admin | To retrive all questions | GET | /api/v1/institutes/{institute_id}/questions | language, Subject, Category, sub category, tags, author, status, complexity, title text | questions basic info
| Admin/Teacher | to retrieve a specific question | GET | /api/v1/institutes/{institute_id}/questions/{id} | language | Questions info, options info, tags info, sub category info
| Admin/Teacher | To update question | PUT | /api/v1/institutes/{institute_id}/questions/{id}
| Admin/Teacher | To only publish a question | PUT | /api/v1/institutes/{institute_id}/questions/{id}/publish
| Admin | to delete a question | DELETE | /api/v1/institutes/{institute_id}/questions/{id}
| Admin/Teacher/Student | To bookmark a question | POST | /api/v1/institutes/{institute_id}/questions/{id}/bookmark
| Admin/Teacher | This endpoint allows you to associate question to subcategories | POST | /api/v1/institutes/{institute_id}/subcategories/{id}/questions_attach | qns id list
| Admin/Teacher | This endpoint allows you to unassociate question to subcategories | POST | /api/v1/institutes/{institute_id}/subcategories/{id}/questions_deattach | qns id list
| Admin/Teacher | This endpoint allows you to associate questions to tag | POST | /api/v1/institutes/{institute_id}/questions_tags_attach | qns id list, tags list
| Admin/Teacher | This endpoint allows you to unassociate questions to tag | POST | /api/v1/institutes/{institute_id}/questions_tags_deattach | qns id list, tags list
Exams | Admin/Teacher | To add/create exam | POST | /api/v1/institutes/{institute_id}/exams
| Admin/Teacher | To retrive my exams | GET | /api/v1/institutes/{institute_id}/me/exams
| Admin/Teacher | To retrive others exmas | GET | /api/v1/institutes/{institute_id}/users/{id}/exams | language, class, author, state, | Exams basic info, sections basic info, class basic info
| Admin/Teacher | To retrive all exams | GET | /api/v1/institutes/{institute_id}/exams | Language, Class, Subject, author, status, complexity, title text | Exams basic info, sections basic info, class basic info
| Student | To retrive all exams per class | GET | /api/v1/institutes/{institute_id}/classes/{id}/exams |  | Exams basic info, sections basic info
| Student | to retrieve a specific exam | GET | /api/v1/institutes/{institute_id}/classes/{id}/exams/{id} |  | Exams basic info, sections info, question count per section
| Admin/Teacher | To update exam | PUT | /api/v1/institutes/{institute_id}/exams/{id}
| Admin | To publish a exam | POST | /api/v1/institutes/{institute_id}/exams/{id}/publish
| Admin | to delete a exam | DELETE | /api/v1/institutes/{institute_id}/exams/{id}
| Admin/Teacher/Student | To bookmark a exam | PUT | /api/v1/institutes/{institute_id}/exams/{id}/bookmark
| Admin/Teacher | to add Section to exam | POST | /api/v1/institutes/{institute_id}/exams/{id}/sections
| Admin/Teacher | to retrieve all sections of a exam | GET | /api/v1/institutes/{institute_id}/exams/{id}/sections
| Admin/Teacher | to update a section | PUT | /api/v1/institutes/{institute_id}/exams/{id}/sections/{id}
| Admin/Teacher | to delete a section | DELETE | /api/v1/institutes/{institute_id}/exams/{id}/sections/{id}
| Admin/Teacher | This endpoint allows you to associate questions to section of a exam | POST | /api/v1/institutes/{institute_id}/exams/{id}/sections/{id}/questions/attach
| Admin/Teacher | This endpoint allows you to unassociate questions to section of a exam | POST | /api/v1/institutes/{institute_id}/exams/{id}/sections/{id}/questions/deattach
| Admin/Teacher | This endpoint allows you to associate exams to class | POST | /api/v1/institutes/{institute_id}/classes/{id}/exams/{id}/attach
| Admin/Teacher | This endpoint allows you to unassociate exam to class | POST | /api/v1/institutes/{institute_id}/classes/{id}/exams/{id}/deattach
Exam Attempts | Student | This endpoint retrieves all attempts for the authenticated user. | GET | /api/v1/institutes/{institute_id}/exams/attempts |  | Exam basic info, attempt info
| Student | This endpoint retrieves the attempts of a user for a particular exam. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts |  | Exam basic info, attempt info
| Student | This endpoint retrieves a single attempt. | GET | /api/v1/institutes/{institute_id}/exams/attempts/{id}
| Student | This endpoint will create a new attempt for the exam. | POST | /api/v1/institutes/{institute_id}/exams/{id}/attempts
| Student | This endpoint starts a paused attempt. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/start
| Student | This is done to update the remaining time for that attempt in the server. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/heartbeat
| Student | This endpoint ends an attempt. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/end
| Student | This endpoint returns all questions for an attempt. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/questions
| Student | This endpoint will update a question with the selected_answers and review. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/questions/{id}
| Student | This endpoint returns all questions for an attempt with correct answer & explanation. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/review | get all questions and answer of exam, get all answers of that attempt - join three in a json and respond
| Student | This endpoint returns subject wise analytics of the attempt. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/review/subjects
Practice | Admin/Teacher | To add/create practices | POST | /api/v1/institutes/{institute_id}/practices
| Admin/Teacher | To retrive my practices | GET | /api/v1/institutes/{institute_id}/practices
| Admin/Teacher | To retrive others practices | GET | /api/v1/institutes/{institute_id}/users/{id}/practices
| Admin/Teacher | To retrive all practices | GET | /api/v1/institutes/{institute_id}/practices | Language, Class, Subject, author, status, complexity, title text
| Student | To retrive all practices per class | GET | /api/v1/institutes/{institute_id}/classes/{id}/practices
| Student | to retrieve a specific practice | GET | /api/v1/institutes/{institute_id}/classes/{id}/practices
| Admin/Teacher | To update practice | PUT | /api/v1/institutes/{institute_id}/practices/{id}
| Admin | To publish a practice | POST | /api/v1/institutes/{institute_id}/practices/{id}/publish
| Admin | to delete a practice | DELETE | /api/v1/institutes/{institute_id}/practices/{id}
| Admin/Teacher/Student | To bookmark a practice | PUT | /api/v1/institutes/{institute_id}/practices/{id}/bookmark
| Admin/Teacher | This endpoint allows you to associate questions to practice | POST | /api/v1/institutes/{institute_id}/practices/{id}/questions/attach
| Admin/Teacher | This endpoint allows you to unassociate questions to practice | POST | /api/v1/institutes/{institute_id}/practices/{id}/questions/deattach
| Admin/Teacher | This endpoint allows you to associate practices to class | POST | /api/v1/institutes/{institute_id}/classes/{id}/practices/{id}/attach
| Admin/Teacher | This endpoint allows you to unassociate practices to class | POST | /api/v1/institutes/{institute_id}/classes/{id}/practices/{id}/deattach
Practice Attempts | Student | This endpoint retrieves all attempts for the authenticated user. | GET | /api/v1/institutes/{institute_id}/practices/attempts
Should we keep all attempts in DB or just last attempt is enough | Student | This endpoint retrieves the attempts of a user for a particular exam. | GET | /api/v1/institutes/{institute_id}/practices/{id}/attempts
| Student | This endpoint retrieves a single attempt. | GET | /api/v1/institutes/{institute_id}/practices/attempts/{id}
| Student | This endpoint will create a new attempt for the practice. | POST | /api/v1/institutes/{institute_id}/practices/{id}/attempts
| Student | This endpoint starts a paused attempt. | PUT | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/start
| Student | This is done to update the remaining time for that attempt in the server. | PUT | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/heartbeat
| Student | This endpoint ends an attempt. | PUT | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/end
| Student | This endpoint returns all questions for an attempt. | GET | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/questions
| Student | This endpoint will update a question with the selected_answers and review. | PUT | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/questions/{id}
| Student | This endpoint returns all questions for an attempt with correct answer & explanation. | GET | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/review
| Student | This endpoint returns subject wise analytics of the attempt. | GET | /api/v1/institutes/{institute_id}/practices/{id}/attempts/{id}/review/subjects
Study Notes | Admin/Teacher | To add/create notes | POST | /api/v1/institutes/{institute_id}/Users/{id}/notes
| Admin/Teacher | To retrive my notes | GET | /api/v1/institutes/{institute_id}/me/notes
| Admin | To retrive others notes | GET | /api/v1/institutes/{institute_id}/users/{id}/notes
| Admin | To retrive all notes | GET | /api/v1/institutes/{institute_id}/notes
| Student | To retrive all notes per class | GET | /api/v1/institutes/{institute_id}/class/{id}/notes
| Admin/Teacher/Student | to retrieve a specific note | GET | /api/v1/institutes/{institute_id}/subcategory/{id}/notes
| Admin/Teacher | To update note | PUT | /api/v1/institutes/{institute_id}/notes/{id}
| Admin | To publish a note | POST | /api/v1/institutes/{institute_id}/notes/{id}/publish
| Admin | to delete a note | DELETE | /api/v1/institutes/{institute_id}/notes/{id}
| Admin/Teacher/Student | To bookmark a note | PUT | /api/v1/institutes/{institute_id}/notes/{id}/bookmark
| Admin/Teacher | This endpoint allows you to associate notes to sub category | POST | /api/v1/institutes/{institute_id}/subcategories/{id}/notes/attach
| Admin/Teacher | This endpoint allows you to unassociate notes to subcategory | POST | /api/v1/institutes/{institute_id}/subcategories/{id}/notes/deattach
Teachers |  | This endpoint retrieves questions added by teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/questions_added
|  | To retrieve exams created by a teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams_added
|  | To retrieve students under a teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/students
|  | To retrieve notes added by a teacher | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes_shared
|  | To retrieve all teachers of an institute | GET | /api/v1/institutes/{institute_id}/Users/teachers
Students |  | To retrieve all teachers of an institute | GET | /api/v1/institutes/{institute_id}/Users/students
|  | To retrieve all teachers of an institute by batch | GET | /api/v1/institutes/{institute_id}/Users/students?batch={user_group}
|  | This endpoint retrieves question practiced | GET | /api/v1/institutes/{institute_id}/Users/{id}/practice_questions_done
|  | This endpoint retrieves exams attempted | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams_attempted
|  | This endpoint retrieves subjects taken | GET
Exams |  | To add/create exam | POST | /api/v1/institutes/{institute_id}/exams
|  | To retrieve exam in draft | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?subject={teacher-subject}$exam_status={draft}
|  | To update an exam | PUT | /api/v1/institutes/{institute_id}/exams/{exam_id}
|  | To schedule an exam | PUT | /api/v1/institutes/{institute_id}/exams/{exam_id} |  | exam_status={published}
|  | To retrieve all exams under institute | GET | /api/v1/institutes/{institute_id}/exams | subject, title
|  | To retrieve all exams under institute upcoming | GET | /api/v1/institutes/{institute_id}/exams/upcoming | subject, title
|  | To retrieve all exams under institute available | GET | /api/v1/institutes/{institute_id}/exams/available | subject, title
|  | This endpoint retrieves all exams (Default) | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&exam_close_time={>current_time}
|  | This endpoint retrieves all exams by type | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&exam_type={exam_type}
|  | This endpoint retrieves all exams by subject | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&subject={subject}
|  | This endpoint retrieves all exams by category | GET | /api/v1/institutes/{institute_id}/Users/{id}/exams?created_by_id={teacher_id}&exam_status={draft, published}&category={category}
To display exams in calender
Exam Attempts |  | This endpoint retrieves all attempts for the authenticated user. | GET | /api/v1/institutes/{institute_id}/attempts
|  | This endpoint retrieves the attempts of a user for a particular exam. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts
|  | This endpoint retrieves a single attempt. | GET | /api/v1/institutes/{institute_id}/attempts/{id}
|  | This endpoint will create a new attempt for the exam. | POST | /api/v1/institutes/{institute_id}/exams/{id}/attempts
|  | This endpoint starts a paused attempt. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/start
|  | This is done to update the remaining time for that attempt in the server. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/heartbeat
|  | This endpoint ends an attempt. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/end
|  | This endpoint returns all questions for an attempt. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/questions
|  | This endpoint will update a question with the selected_answers and review. | PUT | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/questions/{id}
|  | This endpoint returns all questions for an attempt with correct answer & explanation. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/review
|  | This endpoint returns subject wise analytics of the attempt. | GET | /api/v1/institutes/{institute_id}/exams/{id}/attempts/{id}/review/subjects
Practice Attempts |  | This endpoint retrieves all attempts for the authenticated user. | GET | /api/v1/institutes/{institute_id}/practiceattempts
|  | This endpoint retrieves the attempts of a user for a particular practice. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts
|  | This endpoint retrieves a single attempt. | GET | /api/v1/institutes/{institute_id}/practiceattempts/{id}
|  | This endpoint will create a new attempt for the practice. | POST | /api/v1/institutes/{institute_id}/practice/{id}/attempts
|  | This endpoint starts a paused attempt. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/start
|  | This is done to update the remaining time for that attempt in the server. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/heartbeat
|  | This endpoint ends an attempt. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/end
|  | This endpoint returns all questions for an attempt. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/questions
|  | This endpoint will update a question with the selected_answers and review. | PUT | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/questions/{id}
|  | This endpoint returns all questions for an attempt with correct answer & explanation. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/review
|  | This endpoint returns subject wise analytics of the attempt. | GET | /api/v1/institutes/{institute_id}/practice/{id}/attempts/{id}/review/subjects
Study Notes |  | This endpoint add notes | POST | /api/v1/institutes/{institute_id}/Users/{id}/notes
|  | To endpoint retrieve notes in draft | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?author={student_id/teacher_id}$notes_status={draft}
|  | To endpoint update an notes | PUT | /api/v1/institutes/{institute_id}/Users/{id}/notes/{id}
|  | To endpoint retrives a single notes | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes/{id}
|  | This endpoint retrieves all notes (Default) | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?created_by_id={teacher_id}
|  | This endpoint retrieves notes by class | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?user_group={teacher_group/student_group}
|  | This endpoint retrieves notes by type | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?user_group={student_user_group}
|  | This endpoint retrieves notes by subject | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?subject={subject}&user_group={student_user_group}
|  | This endpoint retrieves notes by author | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?teacher={teacher_id}&user_group={student_user_group}
|  | This endpoint retrieves notes added by author | GET | /api/v1/institutes/{institute_id}/Users/{id}/notes?author={student_id/teacher_id}
Evaluation-Stats
Evaluation
UserGroups (Batches) |  | This endpoint retrieves all user_groups | GET | /api/v1/institutes/{institute_id}/user_groups
|  | This endpoint retrieves single user_group | GET | /api/v1/institutes/{institute_id}/user_groups/{id}
|  | This endpoint will create a user_group | POST | /api/v1/institutes/{institute_id}/user_groups
|  | This endpoint will delete specific user_group | DELETE | /api/v1/institutes/{institute_id}/Users/{id}
Institute |  | This endpoint retrieves all classes counts | GET | /api/v1/institutes/{institute_id}/classes_count |  | To populate dashboard
|  | This endpoint retrieves all teachers counts | GET | /api/v1/institutes/{institute_id}/teachers_count |  | To populate dashboard
|  | This endpoint retrieves all students counts | GET | /api/v1/institutes/{institute_id}/students_count |  | To populate dashboard
|  | This endpoint retrieves all subjects counts | GET | /api/v1/institutes/{institute_id}/subjects_count |  | To populate dashboard
|  | This endpoint retreives admin profile | GET | /api/v1/institutes/{institute_id}/admin_profile
|  | This endpoint updates admin profile | PUT | /api/v1/institutes/{institute_id}
|  | This endpoint delete admin profile | DELETE | /api/v1/institutes/{institute_id}
|  | This endpoint adds admin profile | POST | /api/v1/institutes/{institute_id}/admin_profile
|  | This endpoint adds teacher | POST | /api/v1/institutes/{institute_id}/teachers
|  | This endpoint update teacher |  | Already would have covered
|  | This endpoint delete teacher |  | Already would have covered
|  | This endpoint retrieves all teachers |  | Already would have covered
|  | This endpoint retrieves all subjects |  | Already would have covered
|  | This endpoint retrieves all classes counts |  | Already would have covered
|  | This endpoint adds student | POST | /api/v1/institutes/{institute_id}/students
|  | This endpoint bulk add students | POST | /api/v1/institutes/{institute_id}/bulk_students
|  | This endpoint update student |  | Already would have covered
|  | This endpoint delete student |  | Already would have covered
|  | This endpoint retrieves all students counts |  | Already would have covered
Subjects |  |  |  | Already would have covered
Category |  |  |  | Already would have covered
Tags |  |  |  | Already would have covered
Institute Dashboard
SuperAdmin |  | Add Institute |  | Already would have covered
|  | Update Institute |  | Already would have covered
|  | Delete Institute |  | Already would have covered
|  | To retrive all institute | GET | /api/v1/institutes
|  | This endpoint retrieves all institutes counts | GET | /api/v1/institutes_count |  | To populate dashboard
|  | This endpoint retrieves all teachers counts | GET | /api/v1/teachers_count |  | To populate dashboard
|  | This endpoint retrieves all students counts | GET | /api/v1/students_count |  | To populate dashboard
|  | This endpoint retrieves all exams counts | GET | /api/v1/exams_count |  | To populate dashboard
Others
|  | This endpoint get students in class/batch | GET | /api/v1/institutes/{institute_id}/Users?user_group={user_group}

## Overview
1 | Admin